FICTIONAL – FOR TRAINING USE ONLY

# Operational Readiness Note – Project Meridian

Onboarding, cash management, funds flow and loan set-up for Fabrikam

Prepared by Grace Mensah, Head of Client Onboarding & Transaction Services Operations

Tuesday 27 October 2026  |  For the Credit and Compliance Review (chair: Haruka Sato)

# Purpose

This note sets out what Operations needs to put in place if MUFG leads Fabrikam’s €800m acquisition financing, how long each step takes and where the timetable is at risk. It is for this afternoon’s Credit and Compliance Review and the Executive Briefing.

# Summary

Overall status is Amber: nothing so far prevents a closing in Q1 2027, but most workstreams depend on KYC clearance of the target group or on decisions not yet taken. One item is Red: cash pooling including Fabrikam Middle East FZE (UAE) takes 6–8 weeks and is on the critical path for post-closing cash pooling, though not for the closing funds flow.

RAG: Green = on track; Amber = achievable but dependent on others; Red = at risk unless acted on now.

# Status by workstream

| Workstream | Lead time / target | RAG | Comment |
| --- | --- | --- | --- |
| Account opening – Contoso Energy Materials B.V. (Netherlands) | 2–3 weeks after KYC clearance | Amber | Starts once Compliance clears the target group (due 11 Nov) |
| Account opening – Contoso Energy Materials France SAS | 3–4 weeks | Amber | Same dependency on KYC clearance |
| Cash pooling incl. Fabrikam Middle East FZE (UAE) | 6–8 weeks (local documentation, board resolutions, specimen signatures) | Red – critical path | Critical path for post-closing cash pooling; not needed for the closing funds flow |
| Closing funds flow | Plan by 30 Nov | Amber | ≈€1.2bn on closing date; payment cut-offs; multi-party payments |
| Loan administration set-up | Depends on agency role | Amber | Facility agent role to be confirmed |
| Hedging documentation | 3–4 weeks | Amber | ISDA in place with Fabrikam Europe (2019); credit support annex (CSA) amendment needed |

# Asks of the deal team

Start the UAE documentation now, in parallel with KYC, so that cash pooling is ready soon after closing.

Confirm whether MUFG will act as facility agent, so that we can plan the loan administration set-up.

Ask Fabrikam for named contacts in its treasury team for account opening, the funds flow and hedging documentation.

Include Operations in the client follow-up, so that documentation requests reach Fabrikam early.

# Notes

The closing funds flow will move about €1.2bn on the closing date, with several parties paying and receiving funds against fixed payment cut-off times. A written plan by 30 November leaves time to test it well before closing. On hedging, an ISDA master agreement (the standard contract for derivatives such as FX and interest-rate hedges) has been in place with Fabrikam Europe since 2019; only its credit support annex, which governs collateral, needs amending, and that takes 3–4 weeks.

# Key dates ahead

| Date | Milestone and what it means for Operations |
| --- | --- |
| Fri 6 Nov | Indicative, non-binding proposal to Fabrikam; screening results and UAE local account documentation due |
| Wed 11 Nov | Target-group onboarding and UBO confirmation due; Netherlands and France account opening can start once KYC is cleared |
| Thu 12 Nov | Executive Committee decision on Project Meridian |
| Mon 30 Nov | Closing funds-flow plan ready (≈€1.2bn; payment cut-offs; multi-party payments) |
| Mid-December | Target signing (the client has asked whether early December is possible) |
| Q1 2027 | Closing, subject to merger-control approvals; post-closing cash pooling, including the UAE, to follow |